## Overview
LevelUp Quest Platform — Sprint Planning Workbook
Gamified Enterprise Learning Platform ¦ React + .NET + Azure + Dynamics 365 CRM
Project Vision | A gamified enterprise learning platform where users complete quests, earn XP, level up, unlock skills, earn achievements, join guilds, fight boss battles, and track learning progress — integrated with Dynamics 365 CRM and deployed on Azure.
Methodology | Scrum — 14 Sprints (Sprint 0 through Sprint 13), 2-week sprint cadence recommended (~28 weeks total, roughly 7 months).
Tech Stack | Frontend: React + TypeScript. Backend: ASP.NET Core Web API (Clean Architecture: API / Application / Domain / Infrastructure). Database: SQL Server / Azure SQL. Cache: Redis. CRM: Dynamics 365 / Dataverse. Cloud: Azure App Service, Azure Storage, Key Vault, Service Bus, Application Insights. CI/CD: Azure DevOps Pipelines.
Recommended Delivery Approach | Do not design everything upfront. Complete Sprint 0 and Sprint 1 first. Build, test, and deploy each sprint before moving to the next — this mirrors how successful product teams deliver software and builds practical experience across the full stack.
How To Use This Workbook | Sprint Summary = roadmap at a glance. Sprint Backlog = the working task tracker (update Status/% Complete/Actual Hours as work happens). Database Schema = all tables mapped to the sprint that creates them. RACI & Team = role assignment. Risk Register = review every sprint planning & retro. Definition of Done = the quality bar per story. Learning Roadmap = suggested study order.
Color Legend | Yellow-shaded cells are editable tracking fields (Status, % Complete, Actual Hours, Assignee, Notes). All other cells are the fixed plan — edit with care.
KEY METRICS (auto-calculated from Sprint Backlog)
Total Sprints | 14
Total Epics | 14
Total User Stories | 14
Total Tasks | 118
Total Estimated Hours | 443
Total Story Points | 311
Tasks Completed | 0
% Complete | 0%

## Sprint Backlog
Sprint Backlog — Full Task Tracker (118 Tasks)
Yellow columns (Status, % Complete, Assignee, Actual Hours, Notes) are editable tracking fields.
Sprint # | Sprint Name | Epic | User Story ID | User Story | Task ID | Task | Category | Priority | Est. Hours | Story Pts | Status | % Complete | Assignee | Actual Hours | Notes
0 | Sprint 0 - Foundation | Foundation & Project Setup | US-001 | As a developer, I want to create the solution structure, so that development can begin. | T-001 | Create Git repository (mono-repo or multi-repo strategy decision) | DevOps | High | 2 | 1 | Not Started | 0% |  | 0
0 | Sprint 0 - Foundation | Foundation & Project Setup | US-001 | As a developer, I want to create the solution structure, so that development can begin. | T-002 | Create Azure DevOps project (Boards, Repos, Pipelines) | DevOps | High | 2 | 1 | Not Started | 0% |  | 0
0 | Sprint 0 - Foundation | Foundation & Project Setup | US-001 | As a developer, I want to create the solution structure, so that development can begin. | T-003 | Scaffold React application (Vite/CRA + TypeScript template) | Frontend | High | 3 | 2 | Not Started | 0% |  | 0
0 | Sprint 0 - Foundation | Foundation & Project Setup | US-001 | As a developer, I want to create the solution structure, so that development can begin. | T-004 | Scaffold .NET Web API (Clean Architecture: API/Application/Domain/Infrastructure) | Backend | High | 4 | 3 | Not Started | 0% |  | 0
0 | Sprint 0 - Foundation | Foundation & Project Setup | US-001 | As a developer, I want to create the solution structure, so that development can begin. | T-005 | Provision SQL Server database (local + dev instance) | Database | High | 3 | 2 | Not Started | 0% |  | 0
0 | Sprint 0 - Foundation | Foundation & Project Setup | US-001 | As a developer, I want to create the solution structure, so that development can begin. | T-006 | Configure Swagger / OpenAPI documentation | Backend | Medium | 2 | 1 | Not Started | 0% |  | 0
0 | Sprint 0 - Foundation | Foundation & Project Setup | US-001 | As a developer, I want to create the solution structure, so that development can begin. | T-007 | Configure ESLint rules for frontend | Frontend | Medium | 1 | 1 | Not Started | 0% |  | 0
0 | Sprint 0 - Foundation | Foundation & Project Setup | US-001 | As a developer, I want to create the solution structure, so that development can begin. | T-008 | Configure Prettier formatting | Frontend | Medium | 1 | 1 | Not Started | 0% |  | 0
0 | Sprint 0 - Foundation | Foundation & Project Setup | US-001 | As a developer, I want to create the solution structure, so that development can begin. | T-009 | Configure Git branching strategy (GitFlow/trunk-based) + branch policies | DevOps | High | 2 | 1 | Not Started | 0% |  | 0
0 | Sprint 0 - Foundation | Foundation & Project Setup | US-001 | As a developer, I want to create the solution structure, so that development can begin. | T-010 | Set up folder structure: /frontend, /backend, /database, /docs | DevOps | High | 1 | 1 | Not Started | 0% |  | 0
0 | Sprint 0 - Foundation | Foundation & Project Setup | US-001 | As a developer, I want to create the solution structure, so that development can begin. | T-011 | Write project README and contribution guidelines | Docs | Low | 2 | 1 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-012 | Create User entity + EF Core configuration | Backend | High | 3 | 2 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-013 | Create Role entity + EF Core configuration | Backend | High | 2 | 1 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-014 | Create RefreshToken entity + EF Core configuration | Backend | High | 2 | 1 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-015 | Create JWT service (token generation, validation, refresh logic) | Backend | High | 6 | 5 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-016 | Build Register/Login/RefreshToken API endpoints | Backend | High | 5 | 3 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-017 | Implement password hashing (BCrypt/Identity) + validation rules | Backend | High | 3 | 2 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-018 | Build Login Page (React) | Frontend | High | 4 | 3 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-019 | Build Registration Page (React) | Frontend | High | 4 | 3 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-020 | Build Forgot Password Page (React) | Frontend | Medium | 3 | 2 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-021 | Create Users, Roles, UserRoles, RefreshTokens DB tables + migration | Database | High | 3 | 2 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-022 | Implement route guards / protected routes on frontend | Frontend | High | 3 | 2 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-023 | Unit tests: auth service, JWT service | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
1 | Sprint 1 - Authentication | User Authentication | US-002 | As a user, I want to register and log in, so that I can access the platform. | T-024 | QA: end-to-end auth flow testing (register → login → refresh) | QA | High | 3 | 2 | Not Started | 0% |  | 0
2 | Sprint 2 - Character System | Player Profile | US-003 | As a player, I want to view my profile, so that I can track my progress. | T-025 | Design XP/Level formula (L1=0, L2=100, L3=300, L4=600...) | Backend | High | 2 | 1 | Not Started | 0% |  | 0
2 | Sprint 2 - Character System | Player Profile | US-003 | As a player, I want to view my profile, so that I can track my progress. | T-026 | Create PlayerProfiles + Ranks DB tables + migration | Database | High | 3 | 2 | Not Started | 0% |  | 0
2 | Sprint 2 - Character System | Player Profile | US-003 | As a player, I want to view my profile, so that I can track my progress. | T-027 | Build PlayerProfile API (get profile, XP, level, rank) | Backend | High | 4 | 3 | Not Started | 0% |  | 0
2 | Sprint 2 - Character System | Player Profile | US-003 | As a player, I want to view my profile, so that I can track my progress. | T-028 | Build XP calculation & level-up service | Backend | High | 5 | 3 | Not Started | 0% |  | 0
2 | Sprint 2 - Character System | Player Profile | US-003 | As a player, I want to view my profile, so that I can track my progress. | T-029 | Build Avatar upload/selection feature | Frontend | Medium | 4 | 3 | Not Started | 0% |  | 0
2 | Sprint 2 - Character System | Player Profile | US-003 | As a player, I want to view my profile, so that I can track my progress. | T-030 | Build Profile Page UI: avatar, level, XP bar, rank | Frontend | High | 5 | 3 | Not Started | 0% |  | 0
2 | Sprint 2 - Character System | Player Profile | US-003 | As a player, I want to view my profile, so that I can track my progress. | T-031 | Build reusable XP Progress Bar component | Frontend | Medium | 3 | 2 | Not Started | 0% |  | 0
2 | Sprint 2 - Character System | Player Profile | US-003 | As a player, I want to view my profile, so that I can track my progress. | T-032 | Unit tests: XP/level formula edge cases | Backend | Medium | 2 | 1 | Not Started | 0% |  | 0
3 | Sprint 3 - Quest System | Quest Management | US-004 | As a player, I want to complete quests, so that I can gain XP. | T-033 | Create Quests, QuestRewards, UserQuests DB tables + migration | Database | High | 3 | 2 | Not Started | 0% |  | 0
3 | Sprint 3 - Quest System | Quest Management | US-004 | As a player, I want to complete quests, so that I can gain XP. | T-034 | Build Quest CRUD API (admin-managed quests) | Backend | High | 5 | 3 | Not Started | 0% |  | 0
3 | Sprint 3 - Quest System | Quest Management | US-004 | As a player, I want to complete quests, so that I can gain XP. | T-035 | Build Quest completion + reward-granting service (awards XP on completion) | Backend | High | 5 | 3 | Not Started | 0% |  | 0
3 | Sprint 3 - Quest System | Quest Management | US-004 | As a player, I want to complete quests, so that I can gain XP. | T-036 | Implement Daily Quest logic (reset cadence, tracking) | Backend | High | 4 | 3 | Not Started | 0% |  | 0
3 | Sprint 3 - Quest System | Quest Management | US-004 | As a player, I want to complete quests, so that I can gain XP. | T-037 | Implement Weekly Quest logic | Backend | Medium | 3 | 2 | Not Started | 0% |  | 0
3 | Sprint 3 - Quest System | Quest Management | US-004 | As a player, I want to complete quests, so that I can gain XP. | T-038 | Implement Monthly Quest logic | Backend | Medium | 3 | 2 | Not Started | 0% |  | 0
3 | Sprint 3 - Quest System | Quest Management | US-004 | As a player, I want to complete quests, so that I can gain XP. | T-039 | Build Quest Board UI (list, filter by daily/weekly/monthly) | Frontend | High | 6 | 5 | Not Started | 0% |  | 0
3 | Sprint 3 - Quest System | Quest Management | US-004 | As a player, I want to complete quests, so that I can gain XP. | T-040 | Build Quest Detail + Complete Quest UI/interaction | Frontend | High | 4 | 3 | Not Started | 0% |  | 0
3 | Sprint 3 - Quest System | Quest Management | US-004 | As a player, I want to complete quests, so that I can gain XP. | T-041 | Seed sample quest data (e.g., 'Build Login API' = 100 XP) | Database | Low | 2 | 1 | Not Started | 0% |  | 0
3 | Sprint 3 - Quest System | Quest Management | US-004 | As a player, I want to complete quests, so that I can gain XP. | T-042 | QA: quest completion + XP reward integration testing | QA | High | 3 | 2 | Not Started | 0% |  | 0
4 | Sprint 4 - Skill Tree | Skill Progression | US-005 | As a player, I want skill progression, so that I can unlock advanced skills. | T-043 | Create Skills, SkillNodes, UserSkills DB tables + migration | Database | High | 3 | 2 | Not Started | 0% |  | 0
4 | Sprint 4 - Skill Tree | Skill Progression | US-005 | As a player, I want skill progression, so that I can unlock advanced skills. | T-044 | Define skill tree data for React, TypeScript, SQL, .NET, Azure, Dynamics | Backend | Medium | 3 | 2 | Not Started | 0% |  | 0
4 | Sprint 4 - Skill Tree | Skill Progression | US-005 | As a player, I want skill progression, so that I can unlock advanced skills. | T-045 | Build Skill Tree API (get tree, unlock node, prerequisites check) | Backend | High | 6 | 5 | Not Started | 0% |  | 0
4 | Sprint 4 - Skill Tree | Skill Progression | US-005 | As a player, I want skill progression, so that I can unlock advanced skills. | T-046 | Build Skill Unlock service (validates XP/prereqs before unlock) | Backend | High | 5 | 3 | Not Started | 0% |  | 0
4 | Sprint 4 - Skill Tree | Skill Progression | US-005 | As a player, I want skill progression, so that I can unlock advanced skills. | T-047 | Build interactive Skill Tree UI (visual node graph) | Frontend | High | 8 | 8 | Not Started | 0% |  | 0
4 | Sprint 4 - Skill Tree | Skill Progression | US-005 | As a player, I want skill progression, so that I can unlock advanced skills. | T-048 | Build skill node detail/tooltip component | Frontend | Medium | 3 | 2 | Not Started | 0% |  | 0
4 | Sprint 4 - Skill Tree | Skill Progression | US-005 | As a player, I want skill progression, so that I can unlock advanced skills. | T-049 | QA: prerequisite-locking logic testing | QA | Medium | 3 | 2 | Not Started | 0% |  | 0
5 | Sprint 5 - Achievements | Achievements | US-006 | As a player, I want achievements, so that I feel rewarded. | T-050 | Create Achievements, UserAchievements DB tables + migration | Database | High | 2 | 1 | Not Started | 0% |  | 0
5 | Sprint 5 - Achievements | Achievements | US-006 | As a player, I want achievements, so that I feel rewarded. | T-051 | Build Achievement engine (rule-based triggers: first quest, XP milestones, etc.) | Backend | High | 6 | 5 | Not Started | 0% |  | 0
5 | Sprint 5 - Achievements | Achievements | US-006 | As a player, I want achievements, so that I feel rewarded. | T-052 | Build Achievement API (list, unlock, progress) | Backend | High | 4 | 3 | Not Started | 0% |  | 0
5 | Sprint 5 - Achievements | Achievements | US-006 | As a player, I want achievements, so that I feel rewarded. | T-053 | Seed achievements: First Quest, React Beginner, 1000 XP Earned, Azure Explorer, CRM Master | Database | Low | 2 | 1 | Not Started | 0% |  | 0
5 | Sprint 5 - Achievements | Achievements | US-006 | As a player, I want achievements, so that I feel rewarded. | T-054 | Build Achievements Gallery UI (locked/unlocked states) | Frontend | High | 5 | 3 | Not Started | 0% |  | 0
5 | Sprint 5 - Achievements | Achievements | US-006 | As a player, I want achievements, so that I feel rewarded. | T-055 | Build achievement unlock toast/notification animation | Frontend | Medium | 3 | 2 | Not Started | 0% |  | 0
5 | Sprint 5 - Achievements | Achievements | US-006 | As a player, I want achievements, so that I feel rewarded. | T-056 | Unit tests: achievement trigger rules | Backend | Medium | 3 | 2 | Not Started | 0% |  | 0
6 | Sprint 6 - Leaderboard | Competition | US-007 | As a player, I want rankings, so that I can compare my progress. | T-057 | Design leaderboard query strategy (indexing for performance at scale) | Database | High | 3 | 2 | Not Started | 0% |  | 0
6 | Sprint 6 - Leaderboard | Competition | US-007 | As a player, I want rankings, so that I can compare my progress. | T-058 | Build Global Ranking API (paginated, cached) | Backend | High | 5 | 3 | Not Started | 0% |  | 0
6 | Sprint 6 - Leaderboard | Competition | US-007 | As a player, I want rankings, so that I can compare my progress. | T-059 | Build Guild Ranking API | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
6 | Sprint 6 - Leaderboard | Competition | US-007 | As a player, I want rankings, so that I can compare my progress. | T-060 | Build Weekly Ranking API (time-windowed XP) | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
6 | Sprint 6 - Leaderboard | Competition | US-007 | As a player, I want rankings, so that I can compare my progress. | T-061 | Build Leaderboard UI (tabs: Global/Guild/Weekly) | Frontend | High | 5 | 3 | Not Started | 0% |  | 0
6 | Sprint 6 - Leaderboard | Competition | US-007 | As a player, I want rankings, so that I can compare my progress. | T-062 | Add Redis caching for leaderboard queries | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
6 | Sprint 6 - Leaderboard | Competition | US-007 | As a player, I want rankings, so that I can compare my progress. | T-063 | Load testing: leaderboard under concurrent read load | QA | Medium | 3 | 2 | Not Started | 0% |  | 0
7 | Sprint 7 - Guild System | Teams | US-008 | As a player, I want to join guilds, so that I can collaborate with others. | T-064 | Create Guilds, GuildMembers, GuildEvents DB tables + migration | Database | High | 3 | 2 | Not Started | 0% |  | 0
7 | Sprint 7 - Guild System | Teams | US-008 | As a player, I want to join guilds, so that I can collaborate with others. | T-065 | Build Guild CRUD API (create, join, leave, manage roles) | Backend | High | 6 | 5 | Not Started | 0% |  | 0
7 | Sprint 7 - Guild System | Teams | US-008 | As a player, I want to join guilds, so that I can collaborate with others. | T-066 | Build Guild Events API (schedule/track group activities) | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
7 | Sprint 7 - Guild System | Teams | US-008 | As a player, I want to join guilds, so that I can collaborate with others. | T-067 | Build Guild Directory / Search UI | Frontend | High | 4 | 3 | Not Started | 0% |  | 0
7 | Sprint 7 - Guild System | Teams | US-008 | As a player, I want to join guilds, so that I can collaborate with others. | T-068 | Build Guild Detail Page UI (members, events, guild XP) | Frontend | High | 5 | 3 | Not Started | 0% |  | 0
7 | Sprint 7 - Guild System | Teams | US-008 | As a player, I want to join guilds, so that I can collaborate with others. | T-069 | Build Create/Manage Guild UI (admin/leader controls) | Frontend | Medium | 4 | 3 | Not Started | 0% |  | 0
7 | Sprint 7 - Guild System | Teams | US-008 | As a player, I want to join guilds, so that I can collaborate with others. | T-070 | QA: guild membership + permissions testing | QA | Medium | 3 | 2 | Not Started | 0% |  | 0
8 | Sprint 8 - Boss Battles | Major Challenges | US-009 | As a player, I want boss battles, so that I can complete major challenges. | T-071 | Design Boss Battle data model (multi-stage challenge, rewards, requirements) | Backend | High | 3 | 2 | Not Started | 0% |  | 0
8 | Sprint 8 - Boss Battles | Major Challenges | US-009 | As a player, I want boss battles, so that I can complete major challenges. | T-072 | Build Boss Battle API (start, progress, submit, complete) | Backend | High | 6 | 5 | Not Started | 0% |  | 0
8 | Sprint 8 - Boss Battles | Major Challenges | US-009 | As a player, I want boss battles, so that I can complete major challenges. | T-073 | Configure Boss 1: 'Build Full CRUD API' challenge content + validation | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
8 | Sprint 8 - Boss Battles | Major Challenges | US-009 | As a player, I want boss battles, so that I can complete major challenges. | T-074 | Configure Boss 2: 'Deploy to Azure' challenge content + validation | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
8 | Sprint 8 - Boss Battles | Major Challenges | US-009 | As a player, I want boss battles, so that I can complete major challenges. | T-075 | Configure Boss 3: 'Integrate Dynamics CRM' challenge content + validation | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
8 | Sprint 8 - Boss Battles | Major Challenges | US-009 | As a player, I want boss battles, so that I can complete major challenges. | T-076 | Build Boss Battle UI (challenge brief, submission, progress states) | Frontend | High | 6 | 5 | Not Started | 0% |  | 0
8 | Sprint 8 - Boss Battles | Major Challenges | US-009 | As a player, I want boss battles, so that I can complete major challenges. | T-077 | Build Boss defeat celebration/reward UI | Frontend | Low | 3 | 2 | Not Started | 0% |  | 0
8 | Sprint 8 - Boss Battles | Major Challenges | US-009 | As a player, I want boss battles, so that I can complete major challenges. | T-078 | QA: boss battle end-to-end scenario testing | QA | High | 4 | 3 | Not Started | 0% |  | 0
9 | Sprint 9 - Notifications | Communication | US-011 | As a player, I want to receive notifications, so that I stay informed of progress and events. | T-079 | Provision Azure Communication Services (email) | Infra | Medium | 2 | 1 | Not Started | 0% |  | 0
9 | Sprint 9 - Notifications | Communication | US-011 | As a player, I want to receive notifications, so that I stay informed of progress and events. | T-080 | Provision Azure Service Bus (async messaging/queues) | Infra | Medium | 3 | 2 | Not Started | 0% |  | 0
9 | Sprint 9 - Notifications | Communication | US-011 | As a player, I want to receive notifications, so that I stay informed of progress and events. | T-081 | Build Notification service (event-driven: quest complete, level up, achievement) | Backend | High | 6 | 5 | Not Started | 0% |  | 0
9 | Sprint 9 - Notifications | Communication | US-011 | As a player, I want to receive notifications, so that I stay informed of progress and events. | T-082 | Build Email notification templates + sending pipeline | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
9 | Sprint 9 - Notifications | Communication | US-011 | As a player, I want to receive notifications, so that I stay informed of progress and events. | T-083 | Build In-App Notification API + data model | Backend | High | 4 | 3 | Not Started | 0% |  | 0
9 | Sprint 9 - Notifications | Communication | US-011 | As a player, I want to receive notifications, so that I stay informed of progress and events. | T-084 | Build In-App Notification Center UI (bell icon, list, mark-read) | Frontend | High | 5 | 3 | Not Started | 0% |  | 0
9 | Sprint 9 - Notifications | Communication | US-011 | As a player, I want to receive notifications, so that I stay informed of progress and events. | T-085 | Implement Push Notifications (web push / mobile-ready) | Frontend | Low | 4 | 3 | Not Started | 0% |  | 0
9 | Sprint 9 - Notifications | Communication | US-011 | As a player, I want to receive notifications, so that I stay informed of progress and events. | T-086 | QA: notification delivery + reliability testing | QA | Medium | 3 | 2 | Not Started | 0% |  | 0
10 | Sprint 10 - Dynamics 365 CRM | CRM Integration | US-010 | As an administrator, I want player data synchronized to CRM, so that progress can be managed centrally. | T-087 | Design Dataverse schema: Players, Skills, Achievements, LearningProgress tables | Backend | High | 4 | 3 | Not Started | 0% |  | 0
10 | Sprint 10 - Dynamics 365 CRM | CRM Integration | US-010 | As an administrator, I want player data synchronized to CRM, so that progress can be managed centrally. | T-088 | Set up Dynamics 365 / Dataverse environment + service principal auth | Infra | High | 4 | 3 | Not Started | 0% |  | 0
10 | Sprint 10 - Dynamics 365 CRM | CRM Integration | US-010 | As an administrator, I want player data synchronized to CRM, so that progress can be managed centrally. | T-089 | Build Contact Sync integration (player → CRM Contact) | Backend | High | 6 | 5 | Not Started | 0% |  | 0
10 | Sprint 10 - Dynamics 365 CRM | CRM Integration | US-010 | As an administrator, I want player data synchronized to CRM, so that progress can be managed centrally. | T-090 | Build Achievement Sync integration (achievements → Dataverse) | Backend | High | 5 | 3 | Not Started | 0% |  | 0
10 | Sprint 10 - Dynamics 365 CRM | CRM Integration | US-010 | As an administrator, I want player data synchronized to CRM, so that progress can be managed centrally. | T-091 | Build Learning Journey Tracking sync (progress → Dataverse) | Backend | High | 5 | 3 | Not Started | 0% |  | 0
10 | Sprint 10 - Dynamics 365 CRM | CRM Integration | US-010 | As an administrator, I want player data synchronized to CRM, so that progress can be managed centrally. | T-092 | Implement sync error handling, retry logic, and conflict resolution | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
10 | Sprint 10 - Dynamics 365 CRM | CRM Integration | US-010 | As an administrator, I want player data synchronized to CRM, so that progress can be managed centrally. | T-093 | Build Admin CRM Sync Dashboard (status, last sync, errors) | Frontend | Medium | 5 | 3 | Not Started | 0% |  | 0
10 | Sprint 10 - Dynamics 365 CRM | CRM Integration | US-010 | As an administrator, I want player data synchronized to CRM, so that progress can be managed centrally. | T-094 | Integration testing: end-to-end CRM sync scenarios | QA | High | 5 | 3 | Not Started | 0% |  | 0
11 | Sprint 11 - Analytics | Reporting | US-012 | As a stakeholder, I want analytics dashboards, so that I can measure learning outcomes. | T-095 | Build Analytics API: XP Growth over time | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
11 | Sprint 11 - Analytics | Reporting | US-012 | As a stakeholder, I want analytics dashboards, so that I can measure learning outcomes. | T-096 | Build Analytics API: Learning Progress by skill/topic | Backend | Medium | 4 | 3 | Not Started | 0% |  | 0
11 | Sprint 11 - Analytics | Reporting | US-012 | As a stakeholder, I want analytics dashboards, so that I can measure learning outcomes. | T-097 | Build Analytics API: Skill Growth trends | Backend | Medium | 3 | 2 | Not Started | 0% |  | 0
11 | Sprint 11 - Analytics | Reporting | US-012 | As a stakeholder, I want analytics dashboards, so that I can measure learning outcomes. | T-098 | Build Analytics API: Quest/Course Completion Rate | Backend | Medium | 3 | 2 | Not Started | 0% |  | 0
11 | Sprint 11 - Analytics | Reporting | US-012 | As a stakeholder, I want analytics dashboards, so that I can measure learning outcomes. | T-099 | Build Recharts dashboard UI in React app | Frontend | High | 6 | 5 | Not Started | 0% |  | 0
11 | Sprint 11 - Analytics | Reporting | US-012 | As a stakeholder, I want analytics dashboards, so that I can measure learning outcomes. | T-100 | Set up Power BI integration/embedded reports | BI | Medium | 5 | 3 | Not Started | 0% |  | 0
11 | Sprint 11 - Analytics | Reporting | US-012 | As a stakeholder, I want analytics dashboards, so that I can measure learning outcomes. | T-101 | QA: validate analytics data accuracy against source data | QA | Medium | 3 | 2 | Not Started | 0% |  | 0
12 | Sprint 12 - Azure Deployment | Cloud Deployment | US-013 | As a DevOps engineer, I want automated cloud deployment, so that releases are fast and reliable. | T-102 | Provision Azure App Service (frontend + backend hosting) | Infra | High | 3 | 2 | Not Started | 0% |  | 0
12 | Sprint 12 - Azure Deployment | Cloud Deployment | US-013 | As a DevOps engineer, I want automated cloud deployment, so that releases are fast and reliable. | T-103 | Provision Azure SQL (production database) | Infra | High | 3 | 2 | Not Started | 0% |  | 0
12 | Sprint 12 - Azure Deployment | Cloud Deployment | US-013 | As a DevOps engineer, I want automated cloud deployment, so that releases are fast and reliable. | T-104 | Provision Azure Storage (avatars, assets, file uploads) | Infra | Medium | 2 | 1 | Not Started | 0% |  | 0
12 | Sprint 12 - Azure Deployment | Cloud Deployment | US-013 | As a DevOps engineer, I want automated cloud deployment, so that releases are fast and reliable. | T-105 | Configure Azure Key Vault (secrets management) | Infra | High | 3 | 2 | Not Started | 0% |  | 0
12 | Sprint 12 - Azure Deployment | Cloud Deployment | US-013 | As a DevOps engineer, I want automated cloud deployment, so that releases are fast and reliable. | T-106 | Configure Application Insights (monitoring/telemetry) | Infra | Medium | 3 | 2 | Not Started | 0% |  | 0
12 | Sprint 12 - Azure Deployment | Cloud Deployment | US-013 | As a DevOps engineer, I want automated cloud deployment, so that releases are fast and reliable. | T-107 | Build Azure DevOps CI pipeline (build, test, lint) | DevOps | High | 5 | 3 | Not Started | 0% |  | 0
12 | Sprint 12 - Azure Deployment | Cloud Deployment | US-013 | As a DevOps engineer, I want automated cloud deployment, so that releases are fast and reliable. | T-108 | Build Azure DevOps CD pipeline (automated deployment to Dev/Staging/Prod) | DevOps | High | 5 | 3 | Not Started | 0% |  | 0
12 | Sprint 12 - Azure Deployment | Cloud Deployment | US-013 | As a DevOps engineer, I want automated cloud deployment, so that releases are fast and reliable. | T-109 | Configure environment-specific app settings/secrets | DevOps | High | 2 | 1 | Not Started | 0% |  | 0
12 | Sprint 12 - Azure Deployment | Cloud Deployment | US-013 | As a DevOps engineer, I want automated cloud deployment, so that releases are fast and reliable. | T-110 | Production smoke testing + rollback plan validation | QA | High | 4 | 3 | Not Started | 0% |  | 0
13 | Sprint 13 - Enterprise Hardening | Enterprise Features | US-014 | As a platform owner, I want enterprise-grade reliability and security, so that the platform is production-ready. | T-111 | Create AuditLogs table + audit logging middleware | Backend | High | 4 | 3 | Not Started | 0% |  | 0
13 | Sprint 13 - Enterprise Hardening | Enterprise Features | US-014 | As a platform owner, I want enterprise-grade reliability and security, so that the platform is production-ready. | T-112 | Implement Redis caching layer across hot endpoints | Backend | Medium | 5 | 3 | Not Started | 0% |  | 0
13 | Sprint 13 - Enterprise Hardening | Enterprise Features | US-014 | As a platform owner, I want enterprise-grade reliability and security, so that the platform is production-ready. | T-113 | Expand Application Insights monitoring: custom metrics, alerts | DevOps | Medium | 3 | 2 | Not Started | 0% |  | 0
13 | Sprint 13 - Enterprise Hardening | Enterprise Features | US-014 | As a platform owner, I want enterprise-grade reliability and security, so that the platform is production-ready. | T-114 | Implement API rate limiting | Backend | High | 3 | 2 | Not Started | 0% |  | 0
13 | Sprint 13 - Enterprise Hardening | Enterprise Features | US-014 | As a platform owner, I want enterprise-grade reliability and security, so that the platform is production-ready. | T-115 | Run OWASP Top 10 security review + remediation | Security | High | 6 | 5 | Not Started | 0% |  | 0
13 | Sprint 13 - Enterprise Hardening | Enterprise Features | US-014 | As a platform owner, I want enterprise-grade reliability and security, so that the platform is production-ready. | T-116 | Implement security headers (CSP, HSTS, X-Frame-Options, etc.) | Backend | High | 2 | 1 | Not Started | 0% |  | 0
13 | Sprint 13 - Enterprise Hardening | Enterprise Features | US-014 | As a platform owner, I want enterprise-grade reliability and security, so that the platform is production-ready. | T-117 | Full regression test pass across all modules | QA | High | 8 | 8 | Not Started | 0% |  | 0
13 | Sprint 13 - Enterprise Hardening | Enterprise Features | US-014 | As a platform owner, I want enterprise-grade reliability and security, so that the platform is production-ready. | T-118 | Final UAT sign-off + go-live checklist | PM | High | 4 | 3 | Not Started | 0% |  | 0
[5 empty] | TOTALS | (118 tasks) |  |  | 443 | 311 |  |  |  | 0

## Sprint Summary
Sprint Summary — Roadmap At A Glance
14 Sprints ¦ Suggested cadence: 2 weeks per sprint (~28 weeks total)
Sprint # | Sprint Name | Epic Focus | # Tasks | Est. Hours | Story Points | Tasks Done | % Complete | Suggested Duration | Sprint Goal / Definition of Done
0 | Sprint 0 - Foundation | Foundation & Project Setup | 11 | 23 | 15 | 0 | 0% | 1 week | Repo, Azure DevOps project, React app, .NET Web API, SQL DB, linting/formatting, and branching strategy are all in place and buildable.
1 | Sprint 1 - Authentication | User Authentication | 13 | 45 | 31 | 0 | 0% | 2 weeks | A user can register, log in, refresh a JWT, and reset a forgotten password end-to-end; auth unit tests and E2E tests pass in CI.
2 | Sprint 2 - Character System | Player Profile | 8 | 28 | 18 | 0 | 0% | 2 weeks | A player can view their profile with avatar, level, XP bar, and rank; XP/level formula is unit-tested and matches spec.
3 | Sprint 3 - Quest System | Quest Management | 10 | 38 | 26 | 0 | 0% | 2 weeks | Players can view and complete daily/weekly/monthly quests and receive correct XP rewards; quest board is fully functional.
4 | Sprint 4 - Skill Tree | Skill Progression | 7 | 31 | 24 | 0 | 0% | 2 weeks | Players can view an interactive skill tree for React/TypeScript/SQL/.NET/Azure/Dynamics and unlock nodes when prerequisites are met.
5 | Sprint 5 - Achievements | Achievements | 7 | 25 | 17 | 0 | 0% | 2 weeks | Achievement engine triggers correctly on defined events; players see unlocked/locked achievements with unlock animations.
6 | Sprint 6 - Leaderboard | Competition | 7 | 28 | 19 | 0 | 0% | 2 weeks | Global, guild, and weekly leaderboards return correct, cached, and performant rankings under load.
7 | Sprint 7 - Guild System | Teams | 7 | 29 | 21 | 0 | 0% | 2 weeks | Players can create, search, join, and leave guilds; guild events and guild-level XP tracking work correctly.
8 | Sprint 8 - Boss Battles | Major Challenges | 8 | 34 | 26 | 0 | 0% | 2 weeks | All 3 boss battles (Full CRUD API, Deploy to Azure, Integrate Dynamics CRM) are playable end-to-end with correct validation and rewards.
9 | Sprint 9 - Notifications | Communication | 8 | 31 | 22 | 0 | 0% | 2 weeks | Email, in-app, and push notifications fire reliably on key events (quest complete, level up, achievement unlocked).
10 | Sprint 10 - Dynamics 365 CRM | CRM Integration | 8 | 38 | 26 | 0 | 0% | 3 weeks | Player, achievement, and learning-progress data sync reliably to Dataverse with error handling, retries, and an admin sync dashboard.
11 | Sprint 11 - Analytics | Reporting | 7 | 28 | 20 | 0 | 0% | 2 weeks | XP growth, learning progress, skill growth, and completion-rate dashboards are live in-app (Recharts) and in Power BI, with validated data accuracy.
12 | Sprint 12 - Azure Deployment | Cloud Deployment | 9 | 30 | 19 | 0 | 0% | 2 weeks | Application is deployed to Azure (App Service, SQL, Storage, Key Vault, App Insights) via a working CI/CD pipeline with passing smoke tests.
13 | Sprint 13 - Enterprise Hardening | Enterprise Features | 8 | 35 | 27 | 0 | 0% | 2 weeks | Audit logging, Redis caching, rate limiting, and OWASP Top 10 remediation are complete; full regression suite passes and UAT is signed off.
| GRAND TOTAL |  | 118 | 443 | 311 | 0 | 0%

## Database Schema
Database Schema — Table Inventory by Sprint
Sprint Introduced | Table Name | Purpose | Key Relationships
1 | Users | Core user account record (email, password hash, status) | 1:N RefreshTokens, N:N Roles via UserRoles, 1:1 PlayerProfiles
1 | Roles | Application roles (Player, Admin, GuildLeader, etc.) | N:N Users via UserRoles
1 | UserRoles | Join table between Users and Roles | FK → Users, FK → Roles
1 | RefreshTokens | Active/expired JWT refresh tokens per user | FK → Users
2 | PlayerProfiles | Avatar, current level, XP, rank per player | FK → Users, FK → Ranks
2 | Ranks | Rank tiers (e.g., Bronze/Silver/Gold) tied to level/XP thresholds | Referenced by PlayerProfiles
3 | Quests | Quest definitions (title, type: daily/weekly/monthly, description) | 1:N QuestRewards, 1:N UserQuests
3 | QuestRewards | XP/item rewards tied to a quest | FK → Quests
3 | UserQuests | Tracks a user's progress/completion on a quest | FK → Users, FK → Quests
4 | Skills | Skill categories (React, TypeScript, SQL, .NET, Azure, Dynamics) | 1:N SkillNodes
4 | SkillNodes | Individual unlockable nodes within a skill tree, with prerequisites | FK → Skills, self-referencing prerequisite FK
4 | UserSkills | Tracks which skill nodes a user has unlocked | FK → Users, FK → SkillNodes
5 | Achievements | Achievement definitions and unlock rules | 1:N UserAchievements
5 | UserAchievements | Tracks which achievements a user has earned and when | FK → Users, FK → Achievements
7 | Guilds | Guild/team definitions (name, description, guild XP) | 1:N GuildMembers, 1:N GuildEvents
7 | GuildMembers | Membership + role (leader/officer/member) per guild | FK → Guilds, FK → Users
7 | GuildEvents | Scheduled guild activities/events | FK → Guilds
13 | AuditLogs | Immutable log of sensitive actions across the platform | FK → Users (actor), polymorphic entity reference
Note: Dataverse tables (Players, Skills, Achievements, LearningProgress) introduced in Sprint 10 for CRM sync live in Dynamics 365 / Dataverse, not SQL Server — see 'Sprint Backlog' Sprint 10 rows.

## RACI & Team
RACI & Team Allocation
Suggested for a solo learner scaling toward a small team; adjust headcount to your actual team size.
Role | Responsibilities | Sprints Most Involved | Recommended Headcount
Product Owner / PM | Owns backlog priority, sprint goals, stakeholder communication, UAT sign-off | All sprints | 1
Scrum Master | Facilitates ceremonies, removes blockers, tracks velocity | All sprints | 1 (can be shared role)
Frontend Developer (React/TS) | Builds all UI: auth pages, profile, quests, skill tree, leaderboard, guilds, dashboards | 0,1,2,3,4,6,7,8,9,11 | 1-2
Backend Developer (.NET) | Builds APIs, services, business logic, EF Core models, background jobs | 0,1,2,3,4,5,6,7,8,9,10,13 | 1-2
Database Engineer | Schema design, migrations, indexing, performance tuning | 0,1,2,3,4,5,7,10 | 1 (can be shared with backend dev)
DevOps / Cloud Engineer | Azure infra, CI/CD pipelines, Key Vault, monitoring, deployment | 0,9,12,13 | 1
CRM/Dynamics Specialist | Dataverse schema, Dynamics 365 integration and sync logic | 10 | 1 (can be contracted for this sprint)
QA Engineer | Test planning, unit/integration/E2E testing, regression, UAT support | 1,3,4,6,7,8,9,10,11,12,13 | 1
Security Reviewer | OWASP review, security headers, rate limiting sign-off | 13 | 1 (can be shared/consultant)

## Risk Register
Risk Register
Review at every sprint planning session and retrospective. Risk Score = Likelihood (1-5) × Impact (1-5).
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation Strategy | Owner | Status
R-01 | Dynamics 365 / Dataverse integration complexity underestimated (Sprint 10) | Technical | 4 | 4 | 16 | Timebox a spike in Sprint 9 to validate auth + one sync path before Sprint 10 begins; consider a short-term Dynamics specialist. | Backend Lead | Open
R-02 | Scope creep — gamification features (guilds, boss battles) grow beyond MVP | Scope | 4 | 3 | 12 | Lock sprint scope at planning; new ideas go to a backlog for a post-MVP phase, not the current sprint. | Product Owner | Open
R-03 | Azure cost overrun from underused provisioned services | Financial | 3 | 3 | 9 | Use Azure cost alerts/budgets from Sprint 12 onward; right-size App Service/SQL tiers for dev vs prod. | DevOps Lead | Open
R-04 | Leaderboard/Redis performance degrades at scale | Technical | 3 | 3 | 9 | Load test in Sprint 6; add caching and pagination early rather than retrofitting. | Backend Lead | Open
R-05 | Security vulnerabilities found late (only addressed in Sprint 13) | Security | 3 | 5 | 15 | Run lightweight security checks (dependency scanning, basic header checks) every sprint, not just Sprint 13. | Security Reviewer | Open
R-06 | Single-developer bottleneck if built solo without a team | Resourcing | 4 | 4 | 16 | Sequence sprints strictly, protect focus time, and consider pairing/contracting for CRM (Sprint 10) and security (Sprint 13) sprints. | PM | Open
R-07 | Skill tree / boss battle UI complexity slows Sprint 4 and 8 delivery | Technical | 3 | 3 | 9 | Timebox UI exploration; ship a functional (less polished) version first, iterate visuals post-MVP. | Frontend Lead | Open
R-08 | CI/CD pipeline misconfiguration delays first production deploy | Technical | 2 | 4 | 8 | Build and test the pipeline against a throwaway environment in Sprint 0/9, not for the first time in Sprint 12. | DevOps Lead | Open

## Definition of Done
Definition of Done — Quality Bar for Every User Story
Checklist Item | Applies To
Code builds with zero errors/warnings in CI | All stories
Unit tests written and passing for new business logic | Backend/Frontend
API endpoints documented in Swagger/OpenAPI | Backend
Database migrations run cleanly on a fresh environment | Database
UI is responsive and matches design/UX expectations | Frontend
Code reviewed and approved by at least one other developer | All stories
No known Critical/High severity bugs open | All stories
Feature manually tested against acceptance criteria in the User Story | All stories
Security considerations reviewed (auth, input validation, secrets) | Backend/Infra
Deployed and verified in a Dev/Staging environment | All stories
Documentation updated (README, API docs, or runbook) if applicable | All stories
Product Owner has accepted the story against its acceptance criteria | All stories

## Learning Roadmap
Recommended Learning Order
Study just ahead of the sprint that needs it — don't front-load everything before Sprint 0.
# | Topic | Why It Matters Here
1 | React Fundamentals | Needed starting Sprint 0/1 to build every UI screen.
2 | TypeScript | Type safety across the entire React app; used from Sprint 0 onward.
3 | ASP.NET Core Web API | Powers every backend endpoint from Sprint 0 onward.
4 | Entity Framework Core | ORM for all database entities, migrations, and queries.
5 | SQL Server | Underlying relational database; needed for schema design from Sprint 0.
6 | JWT Authentication | Core to Sprint 1's entire authentication system.
7 | Clean Architecture | The layering pattern (API/Application/Domain/Infrastructure) used throughout the backend.
8 | Azure Fundamentals | Baseline cloud literacy needed before Sprint 9/12 infra work.
9 | Azure App Services | Hosting platform for frontend + backend in Sprint 12.
10 | Azure SQL | Production database service used in Sprint 12.
11 | Azure DevOps | Boards/Repos/Pipelines used from Sprint 0 (setup) through Sprint 12 (CI/CD).
12 | Dynamics 365 CRM | Business-user side of the CRM integration built in Sprint 10.
13 | Dataverse | Underlying data platform for Dynamics 365; core to Sprint 10's sync logic.
14 | Power Automate | Useful for lightweight CRM sync/notification automation touched in Sprints 9-10.
15 | Monitoring & Observability | Application Insights and logging practices used in Sprints 9, 12, and 13.